## Timetable
CLIENT LOGO
Open Enrollment Timetable |  |  |  |  | Renewal Date: | 2024-01-01 | Exhibit 2
Financial & Strategy Process |  | Typical Days Needed |  | Actual Date | Who | Completed | Comments
1 | Initial Pre-Renewal Kickoff Meeting/Discussion | 92 | before the renewal date | 2023-10-01 | SI/Client
2 | Census Request to client (or Download if SI has access) | 1 | days after #1 | 2023-10-02 | SI/Client
3 | Census Deadline (if provided by Client) | 7 | after request | 2023-10-09 | Client
4 | Prepare RFP Bid Specs | 3 | after census receipt | 2023-10-12 | SI
5 | Receive Medical and Ancillary Renewal | 70 | before the renewal date | 2023-10-23 | SI |  | BCBSIL is closer to 80, UHC is closer to 60
6 | Update Client on Renewal Status (Email, Call or Meeting) | 2 | after renewal received | 2023-10-25 | SI
7 | Send RFP(s) to Carriers | 2 | after renewal received | 2023-10-25 | SI
8 | RFP Deadline | 14 | after RFP release | 2023-11-08 | SI
9 | Additional Modeling & Carrier Follow-up | 6 | after RFP deadline | 2023-11-14 | SI
10 | Renewal Meeting and Strategy Discussion | 6 | after RFP deadline | 2023-11-14 | SI/Client
11 | Additional Follow-Up with Carriers/Vendors (if needed) | 4 | after First Meeting | 2023-11-18 | SI
12 | Second/Final Renewal Meeting (if needed) | 4 | after First Meeting | 2023-11-18 | SI/Client
13 | Final Decisions - Carrier/Plan Design/Contributions | 3 | after Second Meeting | 2023-11-21 | Client
Open Enrollment
14 | Planning & Design - answer Green Logistics box below |  | same day as decisions | 2023-11-21 | SI/Client
15 | Build Open Enrollment Materials | 5 | after final decisions | 2023-11-26 | SI
16 | Receive SBCs from Carriers | 5 | after final decisions | 2023-11-26 | SI
17 | Client Review Open Enrollment Materials | 2 | after receipt from SI | 2023-11-28 | Client
18 | Renew Ben Admin System | 10 | after final decisions | 2023-12-01 | SI
19 | Client & SI Service Team Test Ben Admin System | 2 | days after BAS updated | 2023-12-03 | SI/Client
20 | Send out Open Enrollment Announcement to Ees | 7 | before OE | 2023-11-29 | Client
21 | Open Enrollment Start | 3 | days after test | 2023-12-06 | SI/Client
22 | Open Enrollment End (soft deadline) | 10 | days | 2023-12-16 | SI/Client
23 | Open Enrollment Final Deadline | 2 | after end date | 2023-12-18 | SI/Client |  |  | Is Timeline OK?
Carrier Enrollment Processing | [7 empty] | OK
24 | Completion/Signatures for all Employer Paperwork | 15 | before Renewal Date | 2023-12-17 | SI/Client
25 | SI Preparation of Open Enrollment Change Spreadsheet | 13 | before Renewal Date | 2023-12-19 | SI
26 | Post OE Census Download from EENav | 15 | before Renewal Date | 2023-12-17 | SI
27 | Submission of Employee Elections to Carriers | 14 | before Renewal Date | 2023-12-18 | SI |  | manual, census file, or feed
28 | Obtain Carrier Approval/Acceptance (if necessary) | 7 | before Renewal Date | 2023-12-25 | SI
29 | Electronic Temporary ID cards available | 2 | before Renewal Date | 2023-12-30 | SI
30 | Cancellation of old plans (if necessary) | 1 | before Renewal Date | 2023-12-31 | SI/Client
31 | Employees to Receive Hard ID cards at home addresses | 1 | before Renewal Date | 2023-12-31 | SI
32 | Effective Date |  |  | 2024-01-01
Client Payroll Processing
32 | Payroll report to client to input into payroll | 3 | before first payroll | 2024-01-01 | SI/Client
33 | Client First Payroll Date for New Deductions |  | varies by client | 2024-01-04 | Client
| OE Logistics |  |  | Option | Comment |  |  |  | Drop Down Options
1 | OE Communication format: |  |  | drop-down |  |  |  |  | Memo (1-pager) | OE Guide | Ben eGuide (new)
2 | OE Content |  |  | drop-down |  |  |  |  | Carrier Change | New Lines of Coverage | EE Costs Only | Combination
3 | OE Meeting format: |  |  | drop-down |  |  |  |  | None | In-Person | Live Zoom | Live Teams | Recorded Zoom | Recorded Teams | Combination
4 | OE Requirement: All, or only those who want to make changes? |  |  | drop-down |  |  |  |  | Active | Passive
5 | Confirm Payroll Vendor |  |  | enter payroll vendor
6 | Enrollment Platform |  |  | drop-down |  |  |  |  | Employee Navigator | enter payroll vendor | Paper | UBenefit | Other
a | if online, is there a blackout period during OE for new hires? |  |  | drop-down
b | if online, are there carrier feeds? |  |  | drop-down |  |  |  |  | Yes | No
c | if there is a current carrier feed, are we changing carriers? |  |  | drop-down
d | if online, is there payroll integration? |  |  | drop-down
7 | Are you implementing or updating Surcharges? |  |  | drop-down
8 | Do you cover Domestic Partners, or only Civil Unions? |  |  | drop-down
9 | Do you have anyone currently on COBRA, or pending? |  |  | drop-down
Formulas:
Actual Date = +G3-[Typical Days Needed]
Actual Date = +[Typical Days Needed]+[Actual Date, row above]